WBOPDC Seal Extension Delivery Plan as at 21 September 2026
	ROAD
	START
(m)
	END
(m)
	LENGTH
(m)
	CURRENT PROJECT PHASE
	INDICATIVE CONSTRUCTION TIMING

	1307 TE PUKE HIGHWAY (MAORI ROADWAY)
	0
	104
	104
	Completed
	n/a

	KYBER PASS
	16
	82
	66
	Completed
	n/a

	GOODALL ROAD (MAORI ROADWAY)
	0
	506
	506
	Landowner consultation
	28/29

	THORN ROAD
	175
	679
	504
	Completed
	n/a

	JESS ROAD
	1154
	1260
	106
	Completed
	n/a

	MCMEEKING ROAD (MAORI ROADWAY)
	20
	506
	486
	Construction
	26/27

	OTAMARAKAU VALLEY ROAD
	6210
	7088
	878
	Completed
	n/a

	STRANG ROAD (MAORI ROADWAY)
	525
	1092
	567
	Landowner consultation
	27/28

	KUMIKUMI ROAD
	0
	1000
	1000
	Completed
	n/a

	KUMIKUMI ROAD
	1000
	2245
	1245
	Completed
	n/a

	WORK ROAD
	6915
	7894
	979
	Construction
	26/27

	WORK ROAD
	7894
	8873
	979
	Construction
	26/27

	JOHNSON ROAD
	745
	1622
	877
	Landowner consultation
	27/28

	ROTOEHU ROAD
	13539
	14539
	1000
	Completed
	n/a

	NO 3 ROAD
	11813
	12813
	1000
	Completed
	n/a

	TAUMATA ROAD
	10016
	11013
	997
	Not started
	28/29

	TE PUKE QUARRY ROAD
	4305
	5225
	920
	Not started
	29/30

	
	
	
	
	
	

	NOTE:
	
	
	
	
	

	The construction timing for each road may be influenced by factors such as the allocated funding, grouping of sites, landowner agreements, extent of earthworks and delivery co-ordination to maximise the investment



